## Sheet1
Time Tracking
| week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | TOTAL | AVERAGE
Lazlo De Bock | 3.5 | 5 | 14.75 | 19.75 | 14 | 15.75 | 14.5 | 14 | 101.25 | 15.4583
Sander Borret | 3.5 | 5 | 9 | 25 | 19 | 23 | 19 | 18 | 121.5 | 18.8333
Niels Van Nimmen | 3.5 | 5 | 10.5 | 16 | 14 | 19 | 13 | 9 | 90 | 13.5833
Katriena Banasik | 3.5 | 10 | 8.25 | 11.75 | 12 | 14.25 | 23.25 | 7.5 | 90.5 | 12.8333
Total Hours | 14 | 25 | 42.5 | 72.5 | 59 | 72 | 69.75 | 48.5 | 403.25
Total Cost | 560 | 1000 | 1700 | 2900 | 2360 | 2880 | 2790 | 1940 | 16130
week 1 | week 1: Brainstormen Concept; week 4: 14; week 6: week 4; week 7: Design |  | 7.75 | week 6 | Design | 4.25 | week 8 | Font-End | 10
| week 7: Font-End |  | 12 |  | Font-End | 7.5 |  | UX/UI | 4
week 2 | week 1: Project Concretiseren; week 4: 20; week 7: Website Back-End |  | 19 |  | UX/UI | 3.5 |  | Eindproduct | 18
| week 1: Planning, Budget & Timesheets; week 4: 5; week 7: Prototype |  | 6 |  | Storyboarding | 0.5 |  | Eindproduct | 9
| week 7: Website Back-End |  | 16 |  | MLP | 23 |  | Front-End | 3
week 3 | week 1: Wireframes; week 4: 3.75; week 7: Planning |  | 1.5 |  | MLP | 19 |  | Branding & Style Guide | 2
| week 1: Design; week 4: 11; week 7: Design |  | 6 |  | Design | 8 |  | Teamleden lastig vallen | 2
| week 1: Research; week 4: 5; week 7: Development |  | 1 |  | Planning | 0.75 |  | Social media | 0.5
| week 1: Website Back-End; week 4: 4; week 7: Reviewing |  | 1.5 |  | Teamleden lastig vallen | 2
| week 1: Schetsen; week 4: 1; week 7: Teamleden lastig vallen |  | 1.75 |  | Social media | 3.5
| Research |  |  | 3.5
| Website Back-End |  |  | 6
| week 1: Reviewing; week 4: 2.75; week 6: week 5; week 7: Design |  | 5 | week 7 | Font-End | 13.75
| week 1: Wireframes; week 4: 3; week 7: Font-End |  | 6.75 |  | UX/UI | 0.75
| week 1: Teamleden lastig vallen; week 4: 2.5; week 7: UX/UI |  | 2.25 |  | Storyboarding | 0
| week 7: Prototype |  | 12 |  | Eindproduct | 19
| week 7: MLP |  | 7 |  | Eindproduct | 13
| week 7: Website Back-End |  | 14 |  | Front-End | 5
| week 7: Design |  | 8.5 |  | Branding & Style Guide | 12
| week 7: Reviewing |  | 2 |  | Teamleden lastig vallen | 2.25
| week 7: Teamleden lastig vallen |  | 1.5 |  | Social media | 4